## Sheet1
Activity Name | Remaining Duration | Start | Finish | BL Project Start | BL Project Finish | Variance - BL Project Finish Date | Total Float | Primary Constraint
Contract Completion CC 19th July | 0 |  | 20-Jul-26* |  | 2026-07-20 | 0 | 0 | Mandatory Finish
ECI Contract award | 0 | 15-Dec-25* |  | 2025-12-15 |  | 0 | 0 | Start On
Planned completion | 0 |  | 2026-07-03 |  | 2026-07-03 | 0 | 0
Start date lead in (Mobilisation) | 10 | 2026-01-07 | 2026-01-20 | 2026-01-07 | 2026-01-20 | 0 | 0
Start date lead in (Mobilisation) | 0 | 07-Jan-26* |  | 2026-01-07 |  | 0 | 0 | Start On or After
Terminal float @10% | 10 | 2026-07-06 | 2026-07-17 | 2026-07-06 | 2026-07-17 | 0 | 0
Design complete | 0 |  | 2026-06-17 |  | 2026-06-17 | 0 | 12
Start on site | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 17
Agreement of baseline GI data and assumptions in relation to GI scope, GBR Reports and Contaminated Land etc. | 8 | 2026-04-10 | 2026-04-21 |  |  |  | 0 | As Late As Possible
Cost Plan Kick Off Meeting | 1 | 2026-04-09 | 2026-04-09 |  |  |  | 0 | As Late As Possible
Design Freeze | 0 | 2026-04-09 |  |  |  |  | 0 | As Late As Possible
Identification of potential advanced works | 8 | 2026-04-10 | 2026-04-21 |  |  |  | 0 | As Late As Possible
Review existing information, site visit etc Inc Review outline design and GI reports and identify any issue | 8 | 2026-04-10 | 2026-04-21 |  |  |  | 0 | As Late As Possible
Explore and agree consenting & 3rd party stakeholder requirements | 5 | 2026-04-29 | 2026-05-06 |  |  |  | 0 | As Late As Possible
Finalise methodology following supplier quote / programme review | 5 | 2026-05-21 | 2026-05-28 |  |  |  | 0 | As Late As Possible
Finalise P6 programme | 10 | 2026-06-05 | 2026-06-18 |  |  |  | 0 | As Late As Possible
Finalise Procurement Strategy & Schedule | 5 | 2026-06-12 | 2026-06-18 |  |  |  | 0 | As Late As Possible
Finalise Procurement Strategy inc recommendations | 5 | 2026-06-05 | 2026-06-11 |  |  |  | 0 | As Late As Possible
Formulate methodology inc TW via buildability workshops (PEP?) | 5 | 2026-04-22 | 2026-04-28 |  |  |  | 0 | As Late As Possible
Formulation of estimate | 35 | 2026-05-07 | 2026-06-25 |  |  |  | 0 | As Late As Possible
Generate high level P6 programme for design & build phases | 8 | 2026-04-24 | 2026-05-06 |  |  |  | 0 | As Late As Possible
Generate R&O Register | 35 | 2026-04-22 | 2026-06-11 |  |  |  | 0 | As Late As Possible
Internal governance | 5 | 2026-06-26 | 2026-07-02 |  |  |  | 0 | As Late As Possible
Produce CEMP | 15 | 2026-06-05 | 2026-06-25 |  |  |  | 0 | As Late As Possible
Produce Construction phase constraints plan | 15 | 2026-06-05 | 2026-06-25 |  |  |  | 0 | As Late As Possible
Produce high risk activites / constraints doc & how they are managed | 10 | 2026-06-05 | 2026-06-18 |  |  |  | 0 | As Late As Possible
Produce Temp Works Schedule | 10 | 2026-05-29 | 2026-06-11 |  |  |  | 0 | As Late As Possible
Pull together sub-contract strategy and preferred suppliers (PEP?) | 5 | 2026-04-29 | 2026-05-06 |  |  |  | 0 | As Late As Possible
Review and identify and gaps with planning, permits,consents, stakeholder management plan | 5 | 2026-05-29 | 2026-06-04 |  |  |  | 0 | As Late As Possible
Seek quotations from supply chain | 15 | 2026-05-07 | 2026-05-28 |  |  |  | 0 | As Late As Possible
Submit to UU | 1 | 2026-07-03 | 2026-07-03 |  |  |  | 0 | As Late As Possible
Procurement Start | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 2
Aggregates - governance | 0 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 0 | 7 | As Late As Possible
Aggregates - lead | 10 | 2026-02-05 | 2026-02-19 | 2026-02-05 | 2026-02-19 | 0 | 7 | As Late As Possible
Concrete - governance | 30 | 2026-03-25 | 2026-05-08 | 2026-03-25 | 2026-05-08 | 0 | 0 | As Late As Possible
Concrete - lead | 20 | 2026-05-11 | 2026-06-08 | 2026-05-11 | 2026-06-08 | 0 | 0 | As Late As Possible
Deveg / tree removal - governance | 10 | 2026-01-21 | 2026-02-03 | 2026-01-21 | 2026-02-03 | 0 | 5
Deveg / tree removal - lead | 15 | 2026-02-04 | 2026-02-24 | 2026-02-04 | 2026-02-24 | 0 | 5
Hoarding - governance | 30 | 2026-01-21 | 2026-03-03 | 2026-01-21 | 2026-03-03 | 0 | 2
Hoarding - lead | 15 | 2026-03-04 | 2026-03-24 | 2026-03-04 | 2026-03-24 | 0 | 2
HRA Survey Support - Issue Contract | 1 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 0 | 7
HRA Survey Support - lead | 1 | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-01-22 | 0 | 7
Piling Design Complete | 0 |  | 2026-04-16 |  |  |  | 64
Secant piling - lead (build) | 35 | 2026-04-17 | 2026-06-08 | 2026-04-17 | 2026-06-08 | 0 | 0
Secant piling - lead (design) | 15 | 2026-03-25 | 2026-04-16 | 2026-03-25 | 2026-04-16 | 0 | 0
Surfacing - governance | 70 | 2026-01-21 | 2026-04-30 | 2026-01-21 | 2026-04-30 | 0 | 19
Surfacing - lead | 25 | 2026-05-01 | 2026-06-08 | 2026-05-01 | 2026-06-08 | 0 | 19
HRA UU Approval | 10 | 2026-01-29 | 2026-02-12 | 2026-01-29 | 2026-02-12 | 0 | 7
HRA (PBA) Produce & Submit Screening Report | 5 | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-29 | 0 | 7
Footpath closure notices - 3 month period (PROW) | 60 | 2026-01-07 | 2026-03-31 | 2026-01-07 | 2026-03-31 | 0 | 17
LA - Streetlight and electrical cable removal review period | 50 | 2026-01-29 | 2026-04-10 | 2026-01-29 | 2026-04-10 | 0 | 1
NRSWA permits | 5 | 2026-02-05 | 2026-02-12 | 2026-02-05 | 2026-02-12 | 0 | 17
Streetlight and electrical cable removal (assumption) | 10 | 2026-04-13 | 2026-04-24 | 2026-04-13 | 2026-04-24 | 0 | 1
Submit streetlight and electrical cable removal request to LA | 6 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-28 | 0 | 1
BT overhead diversions | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Conservation area consent | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
GPR Surveys | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Ground investigations & report | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Land access within the working area | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Third party approvals | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Topographical surveys | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Tree surveys | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Utility searches | 0 |  | 2026-02-13 |  | 2026-02-13 | 0 | 7 | As Late As Possible
Secant piling design | 30 | 2026-01-22 | 2026-03-04 | 2026-01-22 | 2026-03-04 | 0 | 9 | As Late As Possible
Secant piling design approval | 5 | 2026-03-05 | 2026-03-11 | 2026-03-05 | 2026-03-11 | 0 | 9
JMS Response to TQs | 11 | 2026-02-06 | 2026-02-20 | 2026-02-06 | 2026-02-20 | 0 | 0
MAE contract award | 0 |  | 2026-01-20 |  | 2026-01-20 | 0 | 0
MAE design complete | 0 |  | 2026-06-17 |  | 2026-06-17 | 0 | 12
MAE Project Start | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 0
Mobilisation | 6 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-28 | 0 | 0
Project Completion | 0 |  | 2026-06-17 |  | 2026-06-17 | 0 | 12
Review Information and raise RFIs/TQs | 6 | 2026-01-29 | 2026-02-05 | 2026-01-29 | 2026-02-05 | 0 | 0
All existing drawings in dwg format | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 11
Catchment Area EPD (Explosion Protection Document)- Confirmation of Hazardous Substances in existing tank | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 11
Confirmation of detention tank type | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 11
Feasibility Control Philosophy | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 17
Flowrate from existing shaft | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 17
GFR | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 17
Historical as-built drawings | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 11
Historical model? | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 11
Topographical data and drawing from UU | 0 | 2026-01-21 |  | 2026-01-21 |  | 0 | 11
Scope Surveys for scanning of exisiting assets | 6 | 2026-01-29 | 2026-02-05 | 2026-01-29 | 2026-02-05 | 0 | 54
1050mm overflow design | 10 | 2026-02-23 | 2026-03-06 | 2026-02-23 | 2026-03-06 | 0 | 59
GDR | 6 | 2026-02-06 | 2026-02-13 | 2026-02-06 | 2026-02-13 | 0 | 5
Pipe entry/exit details | 6 | 2026-04-13 | 2026-04-20 | 2026-04-13 | 2026-04-20 | 0 | 30
Review available GI for shaft design | 6 | 2026-01-29 | 2026-02-05 | 2026-01-29 | 2026-02-05 | 0 | 5
Shaft design inc. benching, cover slab, pipe entry/exit | 22 | 2026-02-23 | 2026-03-24 | 2026-02-23 | 2026-03-24 | 0 | 0
Civils Pipe Design | 6 | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-21 | 0 | 29
Flowmeter Chamber | 6 | 2026-04-02 | 2026-04-13 | 2026-04-02 | 2026-04-13 | 0 | 29
Valve Chamber | 6 | 2026-03-25 | 2026-04-01 | 2026-03-25 | 2026-04-01 | 0 | 29
Tank kiosk enclosure foundation | 6 | 2026-04-28 | 2026-05-06 | 2026-04-28 | 2026-05-06 | 0 | 19
Digital time | 4 | 2026-01-21 | 2026-01-26 | 2026-01-21 | 2026-01-26 | 0 | 56
Assessment of structure | 6 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-28 | 0 | 54
Routing, design, drawing | 6 | 2026-04-24 | 2026-05-01 | 2026-04-24 | 2026-05-01 | 0 | 21
Outline P&IDs (required for HAZOP) (Piping & Instrument Diagrams) | 6 | 2026-02-05 | 2026-02-12 | 2026-02-05 | 2026-02-12 | 0 | 49
Basis of Design | 11 | 2026-01-29 | 2026-02-12 | 2026-01-29 | 2026-02-12 | 0 | 11
Control Philosophy | 6 | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-20 | 0 | 25
HAZOP and ALM action close out | 11 | 2026-04-01 | 2026-04-17 | 2026-04-01 | 2026-04-17 | 0 | 25
HAZOP and ALM Report - SST & DD&B | 6 | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-27 | 0 | 25
HAZOP and ALM workshop | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 0 | 25
HAZOP and ALM Workshop document pack inc Fire Safety Review record Submission | 6 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-17 | 0 | 25
HAZOP and ALM workshop record | 3 | 2026-03-27 | 2026-03-31 | 2026-03-27 | 2026-03-31 | 0 | 25
Hydraulic Calculations - Emptying - pipe sizing and pump head loss calc | 11 | 2026-02-13 | 2026-02-27 | 2026-02-13 | 2026-02-27 | 0 | 19
Dangerous Substances and Explosive Atmospheres Regulations (DSEAR) Assessment | 11 | 2026-02-13 | 2026-02-27 | 2026-02-13 | 2026-02-27 | 0 | 19
Lifting Register | 6 | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-04-02 | 0 | 34
Material Take Off | 6 | 2026-04-24 | 2026-05-01 | 2026-04-24 | 2026-05-01 | 0 | 21
Mechanical equipment schedule | 6 | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-04-02 | 0 | 34
Obtain Pump Selection | 6 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-17 | 0 | 19
Pump Datasheet | 6 | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-09 | 0 | 19
Pump system curve, complete with selected/purchased pump curve | 6 | 2026-03-18 | 2026-03-25 | 2026-03-18 | 2026-03-25 | 0 | 34
Significant Site Hazard Identification Plan (existing site hazards record/drawing) | 6 | 2026-04-24 | 2026-05-01 | 2026-04-24 | 2026-05-01 | 0 | 21
Mechanical GA drawings - Fluidic Mixer | 4 | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-04-17 | 0 | 21
Mechanical GA drawings - Pumps in Shaft GA and Risers | 4 | 2026-03-25 | 2026-03-30 | 2026-03-25 | 2026-03-30 | 0 | 21
Mechanical GA drawings - Tank Entry Pipe | 4 | 2026-03-31 | 2026-04-07 | 2026-03-31 | 2026-04-07 | 0 | 21
Mechanical GA drawings - Tremie Pipe | 4 | 2026-04-08 | 2026-04-13 | 2026-04-08 | 2026-04-13 | 0 | 21
Pipework layout plan c/w pipework and manhole schedule | 4 | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 0 | 21
Plan and longitudinal sections – rising main from new to old tank | 11 | 2026-03-25 | 2026-04-10 | 2026-03-25 | 2026-04-10 | 0 | 30
Lightning Protection Risk Assessment | 11 | 2026-04-20 | 2026-05-05 | 2026-04-20 | 2026-05-05 | 0 | 20
Network Architecture Drawing | 6 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-17 | 0 | 30
Outline Design - Load Schedule | 4 | 2026-03-18 | 2026-03-23 | 2026-03-18 | 2026-03-23 | 0 | 19
Power Assessments (From SST Deliverables) | 6 | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-03-31 | 0 | 19
Power Supply Assessment – provide data for power application by UU (DNO APPLICATION BY UU) | 11 | 2026-04-01 | 2026-04-17 | 2026-04-01 | 2026-04-17 | 0 | 19
Telemetry schedules (in prescribed format per UU spreadsheet) | 4 | 2026-03-18 | 2026-03-23 | 2026-03-18 | 2026-03-23 | 0 | 30
User Requirement Specification | 11 | 2026-02-23 | 2026-03-09 | 2026-02-23 | 2026-03-09 | 0 | 25
Block Cable Diagram | 6 | 2026-04-01 | 2026-04-10 | 2026-04-01 | 2026-04-10 | 0 | 24
DNO/MCC Main Incomer Kiosk Location Plan | 6 | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-27 | 0 | 19
Single Line Diagram | 6 | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-03-31 | 0 | 24
Client Review of Design Pack | 11 | 2026-05-07 | 2026-05-21 | 2026-05-07 | 2026-05-21 | 0 | 19
Final Submission | 0 |  | 2026-06-08 |  | 2026-06-08 | 0 | 19
Review and update drawings | 11 | 2026-05-22 | 2026-06-08 | 2026-05-22 | 2026-06-08 | 0 | 19
Submission of Outline Design Pack | 0 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0 | 19
Existing Ferry PS shaft | 22 | 2026-01-21 | 2026-02-19 | 2026-01-21 | 2026-02-19 | 0 | 33
1050mm combined sewer overflow | 17 | 2026-02-20 | 2026-03-16 | 2026-02-20 | 2026-03-16 | 0 | 33
Civil's package review & approval | 5 | 2026-03-17 | 2026-03-23 | 2026-03-17 | 2026-03-23 | 0 | 33
Temporary works designs | 44 | 2026-01-21 | 2026-03-23 | 2026-01-21 | 2026-03-23 | 0 | 33
GDR | 22 | 2026-01-21 | 2026-02-19 | 2026-01-21 | 2026-02-19 | 0 | 75
Geotechnical assessment (tank) | 6 | 2026-03-05 | 2026-03-12 | 2026-03-05 | 2026-03-12 | 0 | 66
Davit Arm | 6 | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-03-31 | 0 | 48
Davit arm package review & approval | 5 | 2026-04-01 | 2026-04-09 | 2026-04-01 | 2026-04-09 | 0 | 48
IFC | 11 | 2026-04-10 | 2026-04-24 | 2026-04-10 | 2026-04-24 | 0 | 48
Pipework | 11 | 2026-03-24 | 2026-04-09 | 2026-03-24 | 2026-04-09 | 0 | 44
Rising main package review & approval | 5 | 2026-04-27 | 2026-05-01 | 2026-04-27 | 2026-05-01 | 0 | 43
Valve chamber | 22 | 2026-03-24 | 2026-04-24 | 2026-03-24 | 2026-04-24 | 0 | 33
Air vent package review & approval | 5 | 2026-05-12 | 2026-05-18 | 2026-05-12 | 2026-05-18 | 0 | 33
Storm tank air vent | 10 | 2026-04-27 | 2026-05-11 | 2026-04-27 | 2026-05-11 | 0 | 33
New vehicle turning head | 11 | 2026-01-21 | 2026-02-04 | 2026-01-21 | 2026-02-04 | 0 | 65
New vehicle turning head package review & approval | 5 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-11 | 0 | 65
Ducting | 28 | 2026-04-30 | 2026-06-10 | 2026-04-30 | 2026-06-10 | 0 | 12
Instrumentation package review & approval | 5 | 2026-06-11 | 2026-06-17 | 2026-06-11 | 2026-06-17 | 0 | 12
Kiosk | 28 | 2026-04-30 | 2026-06-10 | 2026-04-30 | 2026-06-10 | 0 | 12
Contract negotiation | 20 | 2025-12-15 | 2026-01-27 | 2025-12-15 | 2026-01-27 | 0 | 12
MTS contract award | 0 |  | 2026-01-27 |  | 2026-01-27 | 0 | 12
MTS design complete | 0 |  | 2026-06-02 |  | 2026-06-02 | 0 | 23
MTS design mobilisation | 6 | 2026-01-28 | 2026-02-04 | 2026-01-28 | 2026-02-04 | 0 | 12
MEICA outline design | 30 | 2026-02-05 | 2026-03-18 | 2026-02-05 | 2026-03-18 | 0 | 12
Client Design Review / Approval | 10 | 2026-04-30 | 2026-05-14 | 2026-04-30 | 2026-05-14 | 0 | 12
Design Approved | 6 | 2026-05-26 | 2026-06-02 | 2026-05-26 | 2026-06-02 | 0 | 21
Incorporate Comments | 6 | 2026-05-15 | 2026-05-22 | 2026-05-15 | 2026-05-22 | 0 | 21
MEICA design submission/approval | 6 | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-04-29 | 0 | 12
MEICA detailed design | 17 | 2026-03-26 | 2026-04-21 | 2026-03-26 | 2026-04-21 | 0 | 12
Produce O&M template/manual | 2 | 2026-06-03 | 2026-06-04 | 2026-06-03 | 2026-06-04 | 0 | 21
ALM | 0 |  | 2026-03-18 |  | 2026-03-18 | 0 | 12
DSEAR submission | 0 |  | 2026-03-18 |  | 2026-03-18 | 0 | 68
HAZCOMM | 0 |  | 2026-02-04 |  | 2026-02-04 | 0 | 17
HAZCON | 0 |  | 2026-02-12 |  | 2026-02-12 | 0 | 11
HAZOP | 0 |  | 2026-03-18 |  | 2026-03-18 | 0 | 12
ALM actions close out | 5 | 2026-03-19 | 2026-03-25 | 2026-03-19 | 2026-03-25 | 0 | 12
DSEAR actions close out | 5 | 2026-03-19 | 2026-03-25 | 2026-03-19 | 2026-03-25 | 0 | 68
HAZCOMM actions close out | 5 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-11 | 0 | 98
HAZCON actions close out | 5 | 2026-02-13 | 2026-02-19 | 2026-02-13 | 2026-02-19 | 0 | 11
HAZOP actions close out | 5 | 2026-03-19 | 2026-03-25 | 2026-03-19 | 2026-03-25 | 0 | 12
Bollard removal | 1 | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 0 | 7
Install additional parking for bowls club | 5 | 2026-03-18 | 2026-03-24 | 2026-03-18 | 2026-03-24 | 0 | 5
Install temporary compound | 4 | 2026-02-19 | 2026-02-25 | 2026-02-19 | 2026-02-25 | 0 | 7
Mobilisation | 2 | 2026-02-13 | 2026-02-17 | 2026-02-13 | 2026-02-17 | 0 | 7
Reinstate old pub car park entrance & relocate benches | 2 | 2026-02-26 | 2026-03-02 | 2026-02-26 | 2026-03-02 | 0 | 7
Set up temporary fencing | 2 | 2026-02-17 | 2026-02-19 | 2026-02-17 | 2026-02-19 | 0 | 7
Site hoarding / segregation at pub car park and site access | 5 | 2026-03-25 | 2026-03-31 | 2026-03-25 | 2026-03-31 | 0 | 5
Site hoarding to working area (Linear Meterage) | 20 | 2026-03-25 | 2026-04-23 | 2026-03-25 | 2026-04-23 | 0 | 2
Site wide vegetation/tree clearance | 6 | 2026-02-25 | 2026-03-04 | 2026-02-25 | 2026-03-04 | 0 | 5
Water supply installation | 5 | 2026-03-25 | 2026-03-31 | 2026-03-25 | 2026-03-31 | 0 | 5
White lining / road markings to pub car park | 1 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-03 | 0 | 7
Widen access to existing road inc. surfacing | 6 | 2026-03-05 | 2026-03-12 | 2026-03-05 | 2026-03-12 | 0 | 5
Widen access to pub car park inc. surfacing | 3 | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 0 | 5
Backfill and compact with type 1 | 3 | 2026-05-18 | 2026-05-20 | 2026-05-18 | 2026-05-20 | 0 | 1
Backfill and regrade around guide wall | 3 | 2026-06-29 | 2026-07-01 | 2026-06-29 | 2026-07-01 | 0 | 0
Compound drainage (Meterage) | 4 | 2026-04-15 | 2026-04-20 | 2026-04-15 | 2026-04-20 | 0 | 5
Excavate and Import aggregates to create working platform and access for pre-dig | 11 | 2026-05-21 | 2026-06-05 | 2026-05-21 | 2026-06-05 | 0 | 1
Further subsoil excavation to piling matt | 4 | 2026-05-12 | 2026-05-15 | 2026-05-12 | 2026-05-15 | 0 | 1
Guide wall construction | 14 | 2026-06-09 | 2026-06-26 | 2026-06-09 | 2026-06-26 | 0 | 0
Import aggregates for initial compound area (1411 t) 70 wagons | 5 | 2026-04-08 | 2026-04-14 | 2026-04-08 | 2026-04-14 | 0 | 5
Pre-dig shaft footprint | 20 | 2026-03-25 | 2026-04-23 | 2026-03-25 | 2026-04-23 | 0 | 2
RC platform Infill | 2 | 2026-07-02 | 2026-07-03 | 2026-07-02 | 2026-07-03 | 0 | 0
Soil strip for initial compound area (882m3) (Store Onsite ??) | 3 | 2026-04-01 | 2026-04-07 | 2026-04-01 | 2026-04-07 | 0 | 5
Topsoil strip and stockpile remaining working area and compound | 10 | 2026-04-27 | 2026-05-11 | 2026-04-27 | 2026-05-11 | 0 | 1