## Sheet1
Activity ID | Activity Name | Remaining Duration | Start | Finish | BL Project Start | BL Project Finish | Variance - BL Project Finish Date | Total Float | Primary Constraint
Flass Lane Early Works Programme - Feb CL32 |  | 91 | 05-Sep-25 A | 2026-07-13 | 2025-09-05 | 2026-01-28 | -114 | 0
Key Dates (Contract) |  | 53 | 05-Sep-25 A | 2026-07-13 | 2025-09-05 | 2026-01-28 | -114 | -53
AMP8-FLL-KD-1160 | (Completion Date) Early Works Contract | 0 |  | 24-Apr-26* |  | 2026-01-27 | -61 | 0 | Mandatory Finish
AMP8-FLL-KD-1010 | Access Date | 0 | 19-Sep-25 A |  | 2025-09-19 |  | 0
AMP8-FLL-KD-1020 | Planned Completion | 0 |  | 2026-07-10 |  | 2026-01-27 | -114 | -53
AMP8-FLL-KD-1000 | Start Date | 0 | 05-Sep-25 A |  | 2025-09-05 |  | 0
AMP8-FLL-KD-1030 | Terminal Float | 0 | 2026-07-13 | 2026-07-13 | 2026-01-28 | 2026-01-28 | -114 | -53
Milestones |  | 0 | 05-Sep-25 A | 16-Oct-25 A | 2025-09-05 | 2025-10-30 | 10
AMP8-FLL-MIL-1040 | Contract Award | 0 |  | 05-Sep-25 A |  | 2025-09-05 | 0 |  | Finish On or After
AMP8-FLL-MIL-1050 | Start date lead in/mobilisation | 0 | 05-Sep-25 A | 18-Sep-25 A | 2025-09-05 | 2025-09-18 | 0
UU Deliverables |  | 0 | 18-Sep-25 A | 16-Oct-25 A | 2025-09-18 | 2025-10-30 | 10
AMP8-FLL-UU-1680 | Client review of site layout | 0 | 10-Oct-25 A | 16-Oct-25 A | 2025-10-24 | 2025-10-30 | 10
AMP8-FLL-UU-1500 | Client Topo & GPR receipt milestone | 0 |  | 18-Sep-25 A |  | 2025-09-18 | 0
AMP8-FLL-UU-1650 | S159/Third Party Access Approved | 0 |  | 18-Sep-25 A |  | 2025-09-18 | 0
AMP8-FLL-UU-1480 | Shaft level and location confirmation (UU) | 0 |  | 18-Sep-25 A |  | 2025-09-18 | 0
Compensation Events |  | 86 | 07-Jan-26 A | 2026-07-10 |  |  |  | 0
CE-3 Further advanced works |  | 86 | 07-Jan-26 A | 2026-07-10 |  |  |  | 0
AMP8-FLAI-CE-1310 | 2.no trial holes to footpath within junction | 0 | 18-Feb-26 A | 20-Feb-26 A
AMP8-FLAI-CE-1280 | 3.no Trial Holes to Flass Lane to footpath and carridgeway | 0 | 13-Feb-26 A | 18-Feb-26 A
AMP8-FLAI-CE-1330 | 3.no Trial Holes to Friarslane/Bridgate Junction | 0 | 23-Feb-26 A | 27-Feb-26 A
AMP8-FLAI-CE-1370 | Arup Design/ Contract execution | 0 |  | 09-Mar-26* |  |  |  | 33 | Finish On or After
AMP8-FLAI-CE-1410 | Arup Pile design spec (GET) | 0 |  | 01-May-26* |  |  |  | 48 | Finish On or After
AMP8-FLAI-CE-1440 | Commence Main Entrance Works | 0 | 2026-05-27 |  |  |  |  | -53
AMP8-FLAI-CE-1160 | Concrete 1 of 2 footpath/ base for office staircase | 0 | 23-Jan-26 A | 23-Jan-26 A
AMP8-FLAI-CE-1240 | Concrete 2 of 2 footpath / base for office staircase | 0 | 02-Feb-26 A | 02-Feb-26 A
AMP8-FLAI-CE-1220 | Concrete front side of office/ welfare for footpath | 0 | 29-Jan-26 A | 29-Jan-26 A
AMP8-FLAI-CE-1250 | Deliver and install new office Cabins + welfare | 0 | 04-Feb-26 A | 09-Feb-26 A
AMP8-FLAI-CE-1290 | Deveg/Hedgerow removal | 0 | 16-Feb-26 A | 17-Feb-26 A
AMP8-FLAI-CE-1200 | Drill, fix and install base plates, timer post and handrail on all office concrete paths + edges | 0 | 28-Jan-26 A | 30-Jan-26 A
AMP8-FLAI-CE-1120 | Excavate and ay 32 mm MDPE water pipe for office/welfare deed, ducting for electric cable | 0 | 20-Jan-26 A | 21-Jan-26 A
AMP8-FLAI-CE-1070 | Excavate and Form road formation for strip footing | 0 | 14-Jan-26 A | 14-Jan-26 A
AMP8-FLAI-CE-1040 | Excavate and Form Strip footing for cabin foundation | 0 | 12-Jan-26 A | 12-Jan-26 A
AMP8-FLAI-CE-1090 | Excavate and form timber shutters for generator | 0 | 16-Jan-26 A | 16-Jan-26 A
AMP8-FLAI-CE-1230 | Excavate and install temp ducting and water supply to shaft | 0 | 30-Jan-26 A | 30-Jan-26 A
AMP8-FLAI-CE-1470 | Excavate/ remove existing path and kerb line | 2 | 2026-05-28 | 2026-05-29 |  |  |  | -53
AMP8-FLAI-CE-1020 | Hoarding | 0 | 07-Jan-26 A | 19-Jan-26 A
AMP8-FLAI-CE-1480 | Import aggregates for road base | 2 | 2026-06-01 | 2026-06-02 |  |  |  | -53
AMP8-FLAI-CE-1030 | Install edge protection | 0 | 09-Jan-26 A | 09-Jan-26 A
AMP8-FLAI-CE-1510 | Install temporary fencing/gates | 3 | 2026-06-09 | 2026-06-11 |  |  |  | -53
AMP8-FLAI-CE-1180 | Install timber ranch style fence around site car park including signage | 0 | 26-Jan-26 A | 30-Jan-26 A
AMP8-FLAI-CE-1490 | Kerbs | 2 | 2026-06-03 | 2026-06-04 |  |  |  | -53
AMP8-FLAI-CE-1350 | Off-hireTemporary welfare | 0 | 27-Feb-26 A | 27-Feb-26 A
AMP8-FLAI-CE-1340 | Paint Timber hoardings | 0 | 27-Feb-26 A | 27-Feb-26 A
AMP8-FLAI-CE-1420 | Planning Consent - Section 278 Approved | 0 |  | 2026-05-26 |  |  |  | -53
AMP8-FLAI-CE-1380 | Planning Consent for main entrance by UU | 0 |  | 18-Mar-26* |  |  |  | -53 | Finish On or After
AMP8-FLAI-CE-1110 | Pour generator base | 0 | 19-Jan-26 A | 19-Jan-26 A
AMP8-FLAI-CE-1050 | Pour strip footing | 0 | 13-Jan-26 A | 13-Jan-26 A
AMP8-FLAI-CE-1100 | Pour strip footing for second cabin foundation | 0 | 19-Jan-26 A | 19-Jan-26 A
AMP8-FLAI-CE-1140 | Prepare 1 of 2 footpath/ base for office staircase | 0 | 21-Jan-26 A | 21-Jan-26 A
AMP8-FLAI-CE-1460 | Remove hedgerow | 1 | 2026-05-27 | 2026-05-27 |  |  |  | -53
AMP8-FLAI-CE-1320 | Remove TM and remobilise to Friars Lane/Bridgate Junction | 0 | 20-Feb-26 A | 20-Feb-26 A
AMP8-FLAI-CE-1300 | Remove TM from Flass Lane and set up on Friars Lane Co-Junction | 0 | 18-Feb-26 A | 18-Feb-26 A
AMP8-FLAI-CE-1360 | Remove TM on Friarslane/Bridgeate Junction | 0 | 27-Feb-26 A | 27-Feb-26 A
AMP8-FLAI-CE-1010 | Reprofile soil bunding | 0 | 07-Jan-26 A | 08-Jan-26 A
AMP8-FLAI-CE-1000 | Restablish site compound | 0 | 07-Jan-26 A
AMP8-FLAI-CE-1400 | Section 278 Review period | 40 | 2026-03-26 | 2026-05-26 |  |  |  | -53
AMP8-FLAI-CE-1450 | Set up TM | 0 | 2026-05-27 |  |  |  |  | -53
AMP8-FLAI-CE-1260 | Set up TM on Flass Lane | 0 | 09-Feb-26 A
AMP8-FLAI-CE-1060 | Stone compound working area | 0 | 13-Jan-26 A | 14-Jan-26 A
AMP8-FLAI-CE-1190 | Stone infill in the middle of the cabin foundations and set concrete flags | 0 | 26-Jan-26 A | 27-Jan-26 A
AMP8-FLAI-CE-1170 | Stone up and prep ramp for disabled ramp access | 0 | 26-Jan-26 A | 26-Jan-26 A
AMP8-FLAI-CE-1150 | Stone up for 1 of 2 footpath / base for office staircase | 0 | 22-Jan-26 A | 22-Jan-26 A
AMP8-FLAI-CE-1210 | Stone up front side of office/ welfare for footpath | 0 | 28-Jan-26 A | 28-Jan-26 A
AMP8-FLAI-CE-1080 | Strip footing | 0 | 16-Jan-26 A | 16-Jan-26 A
AMP8-FLAI-CE-1130 | Strip shutters from Second cabin foundation | 0 | 20-Jan-26 A | 21-Jan-26 A
AMP8-FLAI-CE-1390 | Submit Section 278 | 5 | 2026-03-19 | 2026-03-25 |  |  |  | -53
AMP8-FLAI-CE-1430 | Submit Traffic management request | 0 |  | 2026-05-26 |  |  |  | -53 | As Late As Possible
AMP8-FLAI-CE-1500 | Tarmac | 2 | 2026-06-05 | 2026-06-08 |  |  |  | -53
AMP8-FLAI-CE-1520 | Time risk allowance @ 20% | 21 | 2026-06-12 | 2026-07-10 |  |  |  | -53
AMP8-FLAI-CE-1270 | Trial hole in footpath + carridgeway on Friars Lane + Temp tarmac for 3.no trial holes | 0 | 09-Feb-26 A | 12-Feb-26 A
Procurement |  | 0 | 19-Sep-25 A | 08-Dec-25 A | 2025-09-19 | 2025-10-30 | -27
AMP8-FLL-PROC-1700 | Aggregates | 0 | 19-Sep-25 A | 30-Oct-25 A | 2025-09-19 | 2025-10-30 | 0
AMP8-FLL-PROC-1600 | Hoarding | 0 | 19-Sep-25 A | 14-Nov-25 A | 2025-09-19 | 2025-10-30 | -11
AMP8-FLL-PROC-1710 | HRA | 0 | 19-Sep-25 A | 02-Oct-25 A | 2025-09-19 | 2025-10-02 | 0
AMP8-FLL-PROC-1610 | Plate bearing testing | 0 | 20-Nov-25 A | 08-Dec-25 A | 2025-09-19 | 2025-10-30 | -27 |  | As Late As Possible
AMP8-FLL-PROC-1580 | Soil & drainage | 0 | 19-Sep-25 A | 06-Oct-25 A | 2025-09-19 | 2025-10-23 | 13
AMP8-FLL-PROC-1630 | Traffic management | 0 | 19-Sep-25 A | 24-Oct-25 A | 2025-09-19 | 2025-10-30 | 4
Permits & Approvals |  | 0 | 19-Sep-25 A | 23-Oct-25 A | 2025-09-19 | 2025-10-23 | 0
Client Approvals |  | 0 | 16-Oct-25 A | 23-Oct-25 A | 2025-10-02 | 2025-10-23 | 0
AMP8-FLL-UU-1720 | HAZCON | 0 |  | 16-Oct-25 A |  | 2025-10-02 | -10 |  | As Late As Possible
AMP8-FLL-UU-1750 | HAZCON to mobilisation lead in | 0 | 17-Oct-25 A | 23-Oct-25 A | 2025-10-03 | 2025-10-23 | 0 |  | As Late As Possible
AMP8-FLL-UU-1730 | Shed permit granted | 0 |  | 16-Oct-25 A |  | 2025-10-23 | 5 |  | As Late As Possible
Streetworks & Traffic Management |  | 0 | 19-Sep-25 A | 17-Oct-25 A | 2025-09-19 | 2025-10-23 | 4
AMP8-FLL-ECI-1360 | Consultation with Compliance Officer | 0 |  | 17-Oct-25 A |  | 2025-10-23 | 4
AMP8-FLL-ECI-1640 | Produce and submit Streetworks permit (PAA) | 0 | 19-Sep-25 A | 17-Oct-25 A | 2025-09-19 | 2025-10-23 | 4
AMP8-FLL-ECI-1340 | TTRO Application, Submission and Review period | 0 | 19-Sep-25 A | 17-Oct-25 A | 2025-09-19 | 2025-10-23 | 4
AMP8-FLL-ECI-1660 | TTRO traffic management approval | 0 |  | 17-Oct-25 A |  | 2025-10-23 | 4
HRA |  | 0 | 03-Oct-25 A | 23-Oct-25 A | 2025-10-03 | 2025-10-23 | 0
AMP8-FLL-ECI-1690 | HRA screening review period (UU) | 0 | 20-Oct-25 A | 23-Oct-25 A | 2025-10-17 | 2025-10-23 | 0
AMP8-FLL-ECI-1670 | Produce HRA screening report | 0 | 03-Oct-25 A | 17-Oct-25 A | 2025-10-03 | 2025-10-16 | -1
AMP8-FLL-ECI-1680 | Submit HRA screening report | 0 |  | 23-Oct-25 A |  | 2025-10-16 | -5
Early Works |  | 0 | 18-Sep-25 A | 2026-07-10 | 2025-09-18 | 2026-01-27 | -114 | -53
Temp Works Design |  | 0 | 18-Sep-25 A | 19-Nov-25 A | 2025-09-18 | 2025-10-22 | -20
AMP8-FLL-DED-1550 | Hoarding TWD completion milestone | 0 |  | 17-Oct-25 A |  | 2025-10-22 | 4
AMP8-FLL-DED-1140 | MAE contract award | 0 |  | 18-Sep-25 A |  | 2025-09-18 | 0
AMP8-FLL-DED-1130 | MAE design period | 0 | 19-Sep-25 A | 16-Oct-25 A | 2025-09-19 | 2025-10-16 | 0
AMP8-FLL-DED-1120 | MAE mobilisation | 0 |  | 18-Sep-25 A |  | 2025-09-18 | 0
202510-AMP8-FLL-DED-1160 | MAE ongoing TWD reviews/support | 0 | 17-Oct-25 A | 19-Nov-25 A
AMP8-FLL-DED-1150 | TRA - Time Risk Allowance (20%) | 0 | 17-Oct-25 A | 17-Oct-25 A | 2025-10-17 | 2025-10-22 | 4
AMP8-FLL-DED-1570 | Working platform TWD completion milestones | 0 |  | 17-Oct-25 A |  | 2025-10-22 | 4
Enabling Activities Sitewide |  | 0 | 07-Oct-25 A | 19-Dec-25 A | 2025-10-24 | 2026-01-27 | 15
Duration |  | 0 | 27-Oct-25 A | 19-Dec-25 A | 2025-10-28 | 2026-01-27 | 15
AMP8-FLL-EAW-1430 | Construction duration (LOE) | 0 | 27-Oct-25 A | 19-Dec-25 A | 2025-10-28 | 2026-01-27 | 15
Construction |  | 0 | 07-Oct-25 A | 19-Dec-25 A | 2025-10-24 | 2026-01-27 | 15
AMP8-FLL-EAW-1250 | Aggregates and install piling platform | 0 | 01-Dec-25 A | 05-Dec-25 A | 2025-12-19 | 2026-01-12 | 14
AMP8-FLL-EAW-1220 | Cut and fill to level compound | 0 | 19-Nov-25 A | 28-Nov-25 A | 2025-11-28 | 2025-12-04 | 4
AMP8-FLL-EAW-1350 | Enabling works TRA - Time Risk Allowance (30% Overall) | 0 | 19-Dec-25 A | 19-Dec-25 A | 2026-01-15 | 2026-01-27 | 16
AMP8-FLL-EAW-1240 | Import aggregates and construct compound | 0 | 13-Nov-25 A | 28-Nov-25 A | 2025-12-05 | 2026-01-12 | 19
AMP8-FLL-EAW-1180 | Install cut-off drainage to working area boundary (connection to ext network) | 0 | 17-Nov-25 A | 27-Nov-25 A | 2025-11-12 | 2025-11-20 | -5
AMP8-FLL-EAW-1110 | Mobilise to main compound | 0 | 27-Oct-25 A | 27-Oct-25 A | 2025-10-31 | 2025-10-31 | 4
AMP8-FLL-EAW-1260 | Plate bearing tests | 0 | 09-Dec-25 A | 11-Dec-25 A | 2026-01-13 | 2026-01-14 | 12
AMP8-FLL-EAW-1170 | Pre-entry soil and drainage survey (main compound) | 0 | 07-Oct-25 A | 13-Oct-25 A | 2025-10-24 | 2025-10-30 | 13
AMP8-FLL-EAW-1410 | Remove ext fence and install access gate to field | 0 | 28-Oct-25 A | 30-Oct-25 A | 2025-10-28 | 2025-10-30 | 0
AMP8-FLL-EAW-1190 | Set up temporary fencing | 0 | 03-Nov-25 A | 05-Nov-25 A | 2025-11-03 | 2025-11-04 | -1
AMP8-FLL-EAW-1200 | Site hoarding | 0 | 01-Dec-25 A | 19-Dec-25 A | 2025-11-21 | 2025-12-18 | -1
AMP8-FLL-EAW-1420 | Soil strip and import aggregates for Initial compound area | 0 | 04-Nov-25 A | 13-Nov-25 A | 2025-11-05 | 2025-11-11 | -2
AMP8-FLL-EAW-1210 | Topsoil strip and stockpile | 0 | 11-Nov-25 A | 14-Nov-25 A | 2025-11-21 | 2025-11-27 | 10
Completion |  | 0 | 2026-07-10 | 2026-07-10 | 2026-01-27 | 2026-01-27 | -114 | -53
AMP8-FLL-EAW-1440 | Client acceptance - construction manager sign off | 0 |  | 2026-07-10 |  | 2026-01-27 | -114 | -53
RETIRED |  | 0 | 24-Oct-25 A | 2026-03-02 | 2025-09-19 | 2026-01-14 | -32 | 38
AMP8-FLL-RET-1010 | Retired - Finish | 0 |  | 2026-03-02 |  |  |  | 38
AMP8-FLL-RET-1011 | Retired - Start | 0 | 27-Oct-25 A
October 2025 |  | 0 | 24-Oct-25 A | 24-Oct-25 A | 2025-09-19 | 2025-10-16 | -5
AMP8-FLL-PROC-1590 | RETIRED - Fence removal | 0 | 24-Oct-25 A | 24-Oct-25 A | 2025-09-19 | 2025-10-16 | -5
December 2025 |  | 0 | [5 empty] | 0
January 2026 |  | 0 | 30-Jan-26 A | 30-Jan-26 A | 2026-01-14 | 2026-01-14 | -12
AMP8-FLL-EAW-1270 | Retired - De-mobilisation | 0 | 30-Jan-26 A | 30-Jan-26 A | 2026-01-14 | 2026-01-14 | -12